## Top Sheet
| DPC Risk Register June 2022 |  |  | DPC0622C
Risks owned by the Board and risks rated above 10 in each operational area
Strategic Risks
Risk number | Workplan | Description | Consequence | Type | Owner | Action | Likeli | Impact | PM Score | Trend | timeline | Added to register | last review | next review
2 |  | DPC adversely impacted by 'Brexit' | unkown | strategic | Board | Watching brief - very many unknowns still exist | 4 | 3 | 12 | Reducing | ongoing | 2016-06-01 | 2022-03-01 | 2022-06-01
3 |  | VAT registtation leads to miscalculation | see MG1 | financial | Board | Register for VAT | 2 | 3 | 6 | Decreasing | 2019-03-01 | 2018-09-01 | 2020-11-01 | 2022-03-01 | Removed March 22
4 |  | Internationalisation not sustainable | energies diverted | strategic | Board | International Strategy, pragmatic planning | 3 | 4 | 12 | Stable | 2019-03-01 | 2018-09-01 | 2022-03-01 | 2022-06-01
5 |  | Ipres creates overstretch | energies diverted | strategic | Board / ED | recruit staff, budget carefully | 3 | 4 | 12 | stable | 2022-09-01 | 2021-09-01 | 2022-03-01 | 2022-06-01
6 |  | Conflict destabilises or fragments the DP community | negative reactions to DPC | reputational | Board / ED | Respond to emerging situation | 3 | 2 | 6 | New | ongoing | 2022-03-01 | 2022-03-01 | 2022-06-01
Risks in Community Engagement and Advocacy
AC10 | 1.d.1 | A group of members leave | Member dissatifaction Members leave May deter new members Loss of credibility | reputational | SLM/WK | Champions Programme and Client Relations Management Tools Continue to provide and communicate great services Expand opportunities for Associate member engagement with Board Create annual activity and value plan in advance 3 year contractual membership Better notice of intention to leave Develop additional sources of funding | 3 | 3 | 9 | Stable/Reducing. Big impact but low likelihood which is reducing because of CRM | Ongoing | 2018-03-12 | 2022-03-01 | 2022-06-01 |  | 2019-06-01 | Move to Board
Risks in Workforce Development
No risks > 10
Risks in Research and Practice
No risks > 10
Risks in Management and Governance
c1 | 6.a.2 6.b.2 | Organisational overstretch - staff capacity is insufficient to deliver on strategic objectives | Strategic objectives not delivered Demotivated staff High staff turnover | Operational | WK | Clear workplans linked to strategic plan Additional staff recruited Regular face to face staff meetings Staff handbook regularly updated Monitor implementation of CPD training allocation Shared files and resources Annual appraisal process 'How To' guides for key financial and comms activity | 3 | 4 | 12 | Stable: appointments made and documentation enhanced through recent handover. | Annual | 2009-11-23 | 2022-03-01 | 2022-06-01

## Community & Advocacy
Community Engagement & Advocacy |  |  |  |  | Likelihood 12 months |  |  |  |  | Likelihood 12 months | [7 empty] | Comment
Risk number | Work plan | Description | Type | Consequence | Raw Likelihood | Raw Impact | Raw Score | Mitigation | Owner | PM Likelihood | PM Impact | PM Score | Overall trend | Time profile | Date Recorded | Last Review | Next Review
AC10 | 1.c.1 | A group of members leave | Reputational | loss of credibility May deter new members | 3 | 5 | 15 | Champions Programme and Client Relations Management Tools Continue to provide and communicate great services Expand opportunities for Associate member engagement with Board Create annual activity and value plan in advance 3 year contractual membership Better notice of intention to leave Develop additional sources of funding | SLM/WK | 3 | 3 | 9 | Stable/Reducing Also CRM and Chamoions in place | Ongoing: sudden | 2009-11-05 | 2022-03-01 | 2022-06-01 | Investigate Champions Programme
AC1 | 1.a.1 1.b.2 | Failure to communicate effectively (two-way) with members (losing or shallowing relationships) | Operational | Mismatch between member needs and DPC offering Loss of credibility Member dissatisfaction | 3 | 4 | 12 | Maintain multiple communications channels: Maintain DPC blog Members Lounge Task Forces/Working Groups Annual un-conference Fail Club Undertake annual review of effectiveness Annual Members Unconference Local hubs (i.e. Australasia) | SLM | 2 | 4 | 8 | Increasing: with growith of membership effective communications becomes more challenging | ongoing | 2018-03-12 | 2022-03-01 | 2022-06-01 | Merges previous refs AC1 AC2 AC3 AC4
AC18 | 2.b.1 | Hostile policy environment to enabling digital preservation (e.g. GDPR) | Environmental | loss of impact lack of integration of DP with wider organisation | 4 | 3 | 12 | Identify needs and blockers, and develop impactful resources to support (i.e. Bit List, Exec Guide, Toolkits) Articulate need clearly and frequently to policy makers Support members to make the case Facilitate knowledge exchange between members Ensure sufficient time, resources and support are in place to develop the resource | SLM | 2 | 4 | 8 | Stable: with introduction of supporting resources | ongoing | 2017-05-12 | 2022-03-01 | 2022-06-01 | Merges AC18 AC15 and AC19
AC11 | 1.c.1 | Inability to discern a meaningful Supporter program | Reputational | May deter new Supporters or result in loss of existing Supporters loss of credibility - parts of the marketplace 'unknown' | 3 | 4 | 12 | Provide and communicate good opportunities to engage with the membership Create annual activity and value plan in advance Aim for 3 year contractual supportership Better notice of intention to leave Develop additional sources of funding | SLM/WK | 2 | 3 | 6 | Increasing: more Supporters makes this increasingly difficult | Ongoing | 2018-03-12 | 2022-03-01 | 2022-06-01
AC16 | 2.b.1 | Failure to engage with global public policy | Reputational | loss of impact loss of opportunity failure to connect with 'big themes' Loss of credibility | 2 | 5 | 10 | Ongoing, regular and systematic review through membership to ensure understanding of public policy landscape Regular reminders to membership | SLM/WK | 2 | 3 | 6 | Increasing: as membership grows, harder to keep track of global policy | ongoing | 2009-11-05 | 2022-03-01 | 2022-06-01
AC6 | 1.c.1 | Lack of understanding of digital preservation sector and digital preservation within other (strategic) sectors | Operational | Loss of revenue Loss of credibility Limited growth and sustainability | 3 | 2 | 6 | Ongoing assessment of DPC event attendees Develop engagement strategy by sector Target specific sectors with direct communications | SLM/WK | 3 | 2 | 6 | Stable | ongoing | 2016-04-01 | 2022-03-01 | 2022-06-01
AC12 | 1.c.1 | Competition for membership emerges | Reputational | Harder to articulate distinctiveness of DPC Reduction in 'market' | 2 | 3 | 6 | Strategic alliances and clarity of purposes Develop outstanding reputation Remain outward looking and flexible | SLM/WK | 2 | 3 | 6 | Stable: Low risk | ongoing | 2009-11-05 | 2022-03-01 | 2022-06-01 | Investigate Champions Programme
AC17 | 2.b.1 | Disagreements over policy consultation | Operational | loss of impact loss of members loss of coherence | 2 | 3 | 6 | Clarity of scope and purpose Clarity of roles Timely intervention Foresight of policy development | SLM/WK | 2 | 3 | 6 | Stable: low risk | ongoing | 2010-07-01 | 2022-03-01 | 2022-06-01
AC22 | 2.d.2 | Failure to deliver impactful advocacy and awareness raising campaigns (i.e. Bit List, Digital Preservation Awards, WDPD) | Reputational | loss of impact loss of opportunity failure to connect with 'big themes' Loss of credibility | 3 | 3 | 9 | Ensure sufficient time, resources and support are in place to develop a deliverable programme | SLM | 2 | 3 | 6 | Reducing: with adequate support | annual | 2018-03-12 | 2022-03-01 | 2022-06-01 | Merges previous refs AC22 AC20 AC23
AC5 | 1.c.1 | Failure to create attractive membership offering | Reputational | Difficulty in maintaining spend Amplification of other risks Inability to expand capacity | 3 | 4 | 12 | Retain high profile of activities Create new resources Continue to deliver great services to members Clear membership proposition | SLM/WK | 1 | 4 | 4 | Reducing at present: needs to be maintained | ongoing | 2009-11-05 | 2022-03-01 | 2022-06-01 | Investigate Champions Programme
AC7 | 1.c.1 | Failure of relationships with existing and emerging and related communities | Reputational | Loss of impact Loss of credibility | 3 | 3 | 9 | Maintain communication with partners Monitor activity worldwide and seek new partners Attend relevant conferences and events | SLM/WK | 1 | 3 | 3 | Stable | ongoing | 2016-04-01 | 2022-03-01 | 2022-06-01
AC24 | 2.d.2 | Failure to engage digital preservation community through campaigns | Reputational | loss of impact loss of opportunity Loss of credibility | 4 | 3 | 12 | Maintain high profile of DPC activities through effective communications Continue to highlight benefits for the digital preservation community Seek feedback from community and adapt programme to best suit needs | SLM | 1 | 3 | 3 | Stable: Requires ongoing work to maintain | ongoing | 2018-03-12 | 2022-03-01 | 2022-06-01
From R&P
CB2 | 4b | Member support demands disproportionate | operational | Reputation Loss of opportunity Impact on staff | 4 | 3 | 12 | Communicate clear roadmap of member support monitor support Offer paid for consultancy to supplement 'pro bono' support Manage/track member support work delivered | PRW | 1 | 2 | 2 | Mostly steady, with some peaks of demand | Annual | 2009-11-05 | 2018-09-11 | Next SC meeting | Relates to insufficient capacity (M&G). Also relates to A&C - keeping in touch with members
CB5 | 4b, 4c | Loss of relevance in light of changing needs of members | environmental | Loss of members Loss of credibility Poor participation in programme | 1 | 4 | 4 | Good feedback mechanisms between DPC and members Maintain good understanding of member needs | PRW | 1 | 2 | 2 | reducing: good consultation | Ongoing Gradual | 2009-11-05 | 2018-09-11 | Next SC meeting | A&C owns this one - connecting the bits etc
CB12 | n/a | Failure to differentiate between DPC service offering for full and associate members and/or provide sufficient additional value to full members | operational | Loss of full members Loss of credibility/reputation Impact on direction of DPC | 3 | 4 | 12 | Clear articulation of services provided Review services, and ensure they remain relevant and effective | PRW | 1 | 2 | 2 | stable | Ongoing gradual | 2018-04-03 | 2018-09-11 | Next SC meeting | Not for R&P - move to M&G or A&C
CB13 | 3d3+ | Failure to deliver DPC services to international members, due to lack of local access to events and networking | operational | Loss of international members Impact on expansion and recruitment of international members | 4 | 4 | 16 | Ensure access to DPC services is considered at every stage of their conception, planning, delivery and review Continue to develop and review recording and streaming for events | PRW | 1 | 2 | 2 | Reducing | Ongoing gradual | 2018-04-03 | 2018-09-11 | Next SC meeting | Think this may be best moved to A&C - potential change to cover membership
CB6 | n/a | Digital preservation is fixed | environmental | Loss of organisational mission | 1 | 4 | 4 | Develop scenario plans and celebrate achievement | PRW | 1 | 1 | 1 | stable | Ongoing Gradual | 2009-11-05 | 2018-09-11 | Next SC meeting | delete this. Or link with A&C - potentially a comms issue

## Workforce Dev - Risk
Workforce Development Risks
[5 empty] | Likelihood 12 months |  |  |  |  | Likelihood 12 months
Risk number | Workplan | Description | Type | Consequence | Raw Likelihood | Raw Impact | Raw Score | Mitigation | Owner | PM Likelihood | PM Impact | PM Score | Overall trend | Time profile | Date Recorded | Last Review | Next Review
WD01 | 3.b.1, 3.e.1 | Unable to attract audience | Operational | loss of impact loss of members loss of income loss of coherence perception | 4 | 4 | 16 | Ensure events fit members needs Advertise events on all relevant comms channels Maintain relationships with partner orgs for shared promotion Keep attendance costs competitive | SMM | 1 | 3 | 3 | Stable | Ongoing, gradual | 2016-11-08 | 2022-05-01 | 2022-08-01
WD02 | 3.c.1, 3.c.2 | Members do not submit scholarship applications | Operational | Loss of impact Loss of members Loss of credibility Poor participation in programme | 4 | 3 | 12 | Ensure scholarships meet members needs Ensure opportunities are relevant and timely Offer travel support where appropriate Promote programme on all relevant channels | SMM | 2 | 3 | 6 | Stable | ongoing, gradual | 2016-11-08 | 2022-05-01 | 2022-08-01
WD03 | 3.c.1 | Unable to identify suitable scholarship opportunities | Operational | loss of impact loss of members perception | 4 | 4 | 16 | Diversify types of opportunities offered Maintain relationships with training proividers | SMM | 2 | 3 | 6 | Stable | ongoing, gradual | 2016-11-08 | 2022-05-01 | 2022-08-01
WD04 | 3.a.2 | Training projects overtake core work | Operational | Loss of capacity Loss of member engagement Mission creep impact on staff | 4 | 4 | 16 | Control by Management Oversight by board Match projects to strategic plan Fully funded projects | SMM | 1 | 4 | 4 | Stable | Start of projects | 2010-07-01 | 2022-05-01 | 2022-08-01
WD05 | 3.b.1, 3.b.2 | Loss of relevance of training and training materials through changes in technology/best practice or members' needs | Environmental | Loss of credibility Loss of impact Loss of members Poor participation in training | 2 | 3 | 6 | Regular review and updates to training materials Ongoing technology watch/consultation witl DPC colleagues Good feedback mechanisms between DPC and members Report quality metrics from all events Monitor key developments in DP community | SMM | 1 | 3 | 3 | stable | Ongoing | 2009-11-05 | 2022-05-01 | 2022-08-01
WD06 | 3.d.1 | Failure to understand labour market | Reputational | Loss of impact Loss of members Loss of credibility | 4 | 2 | 8 | Monitor job postings Report on trends | SMM | 2 | 2 | 4 | stable | Ongoing | 2016-11-08 | 2022-05-01 | 2022-08-01

## Research and Practice
Capacity Building, Good Practice and Standards |  |  |  |  | Likelihood 12 months |  |  |  |  | Likelihood 12 months
Risk number | Work Plan | Description | Type | Consequence | Raw Likelihood | Raw Impact | Raw Score | Mitigation | Owner | PM Likelihood | PM Impact | PM Score | Overall trend | Time profile | Date Recorded | Last Review | Next Review
CB1 | 4b+ | Quality of advice does not meet expected level | operational | Loss of impact Loss of members Loss of coherence Loss of credibility | 2 | 3 | 6 | Clarity of scope and purpose Clarity of roles Timely intervention Facilitate knowledge sharing and ensure advice is based on experience, staff development, internal peer review Managing Member expectations - there is no single right answer. Making our position clear on website and in new Member inductions. | PRW | 2 | 3 | 6 | modest increase: delays with RDBMS sub-project | ongoing sudden | 2010-07-01 | 2022-03-01 | 2022-06-01
CB2 | 4a, 5a | Failure to stay at the 'cutting edge' of digital preservation research and practice | environmental | Loss of credibility Less attractive for members Less impactful support | 2 | 4 | 8 | Participation and attendance at conferences etc Pursue appropriate research and development opportunities Ensure DPC team aware and kept involved in cutting edge work, understanding where the cutting edge is | PRW | 1 | 2 | 2 |  | Ongoing Gradual | 2009-11-05 | 2022-03-01 | 2022-06-01
CB3 | 3.2 | DPC unable to engage in standards development initiatives (eg: not invited, insufficient capacity, effective targetting) | operational | Loss of credibility, Loss of reputation, missed chance to influence, missed value to Members | 3 | 3 | 9 | Standards watch, engage help/represent needs of Members as appropriate, carefully prioritise available effort | JLM | 2 | 3 | 6 | reducing | ongoing | pre 11/05/2020 | 2022-03-01 | 2022-06-01
CB4 |  | Failure to understand members' current and future digital preservation needs | operational | Loss of members, loss of credibility, missed opportunity to provide appropriate events/services | 2 | 4 | 8 | DPC RAM, Connecting the Bits process, regular engagement with Members, attendance at relevant conferences/events | JLM | 1 | 3 | 3 | reducing | ongoing | pre 11/05/2020 | 2022-03-01 | 2022-06-01
CB5 | 3.4 | Failure to develop adequate digital preservation and community knowledge to enable appropriate links to be made between Members | operational | Less impactful support | 2 | 4 | 8 | DPC RAM, Connecting the Bits process, regular engagement with Members, attendance at relevant conferences/events, engagement with social media and blogs | PRW | 1 | 3 | 3 | same but potential to increase as membership grows | ongoing | pre 11/05/2020 | 2022-03-01 | 2022-06-01
CB6 |  | Our research and project work is not aligned with DPC objectives | operational | Loss of credibility, less attractive to members | 3 | 4 | 12 | Approval for new projects/developments sought from DPC board, sub committees regularly consulted and engaged. | PRW | 2 | 3 | 6 | same | ongoing | pre 11/05/2020 | 2022-03-01 | 2022-06-01

## Management & Governance
Management & Governance Risks | [5 empty] | Likelihood within 12 months |  |  |  |  | Likelihood within 12 months
Risk number | Work plan | Description | Old ref | New type | Consequence | Raw Likelihood | Raw Impact | Raw Score | Mitigation | Owner | PM Likelihood | PM Impact | PM Score | Overall trend | Time profile | Date Recorded | Last Review | Next Review
F1 | 6.b.1/2/4 6.e.1/2 | Financial sustainability - Finances are insufficient to meet ongoing operational expenses | MG2, MG8 | Financial | Organisational failure | 3 | 5 | 15 | Extend budget and forecasting horizon Devlop acurate projections and review regularly Maintain an appropriate level of reserves Build in an annual contingency of 10% of budgeted expenditure | JM | 2 | 4 | 8 | Decreasing: forecast improving | Ongoing | 2019-11-11 | Reviewed at each M&G sub-committee and Board meeting
F2 | 6.a.2 6.b.2/3/4 | Financial mismanagement - Finances are improperly managed within annual reporting cycles | MG1, MG14 | Financial | Oranisational failure; Legal penalties; Reputational consequences | 3 | 5 | 15 | Clear procedures and compliance Separation of roles Regular scrutiny of mamagement accounts by Executive Director and Board Annual audit | JM | 2 | 3 | 6 | Stable: clean audit with new auditors | Ongoing | 2019-11-11 | Reviewed at each M&G sub-committee and Board meeting
F3 | 6.a.2 6.b.2 | VAT miscalculation on account of complexity and new registration | MG1 | Financial | Need to charge VAT on subscriptions Loss in revenue Need to repay prevous years' unpaid VAT (4 year limit would be £227,615) | 3 | 4 | 12 | Careful financial planning Now VAT registered Specialist advice sought and consult with partners Clarity received on VATable activity | JM | 3 | 3 | 9 | decreasing: VAT registered building experience | Ongoing | 2019-11-11 | 2022-03-01 | 2022-06-01
F4 | 6.a.2 6.d.1/3 6.e.1 | Income diversity - Loss of memberships has an excessively negative impact on overall budget | MG3, MG6, MG7, MG9, MG10 | Financial | Loss of revenue Inability to maintain staff levels Inability to deliver strategic plan | 2 | 3 | 6 | Introduction of commercial sponsors category Identify and target potential sponsors and revenue streams Develop consultancy offering that supports strategic objectives Involve all staff Partnership and sustainability programme to retain membership | WK | 3 | 3 | 9 | Decreasing: members retained and 20-21 targets met | Ongoing | 2019-11-11 | 2022-03-01 | 2022-09-01
S1 | 5.c.1 | Core strategic focus - Strategic priorities are misaligned with aims and objectives of the organisation | New | Strategic | Annual workplan fails to deliver member benefits; organisation loses focus and fails to address core mission | 3 | 4 | 12 | Consult members annually about priorities Listen to member feedback about events and offerings Review progress on workplan at Board and sub-committee meetings Develop new strrategic plan in consultation with members | WK | 2 | 3 | 6 | More members engaging | Annual | 2019-11-11 | 2022-03-01 | 2022-06-01
S2 | 5.d.4 | Internationalization - Failure to implement the internationalization strategy effectively | MG20, MG21, MG22 | Strategic | Negaitve impact on existing operations; loss of credibility; loss of revenue | 4 | 5 | 20 | Clear contracts with binding financial commitment Clear work plan and objectives with iterative planning Regular detailed reporting on work plan and budgets Regular communication and all staff involvement | WK | 3 | 5 | 15 | Uncertain: new venture and impact of pandemic | Ongoing | 2019-11-11 | 2022-03-01 | 2022-06-01
S3 | 6.a.1/2 6.d.1 | Insufficient members - Failure to maintain and grow the membership | MG3, MG9, MG10 | Strategic | Loss of target audience; loss of credibility/relevance; disproportionate loss of revenue | 3 | 4 | 12 | Provide really great services Expand full membership Create annual activity and value plan in advance 3 year contractual membership Better notice of intention to leave Develop additional sources of funding Balance revenue streams more evenly between full and associate members | WK/JM | 2 | 2 | 4 | reducing: balance between Full and Associates has shifted and budgeted income achieved this year | Ongoing | 2019-11-11 | 2022-03-01 | 2022-09-01
C1 |  | Organisational overstretch - staff capacity is insufficient to deliver on strategic objectives | MG4, MG6 | Capacity | Strategic objectives not delivered Demotivated staff High staff turnover | 3 | 5 | 15 | Clear workplans linked to strategic plan Additional staff recruited Regular face to face staff meetings Staff handbook regularly updated Monitor implementation of CPD training allocation Shared files and resources Annual appraisal process 'How To' guides for key financial and comms activity | JM/WK | 3 | 4 | 12 | Decreasing: Staff stable and recruiting new member | Ongoing | 2019-11-11 | 2022-03-01 | 2022-06-01
C2 | 6.d.2 | Global pandemic (eg coronavirus) prevents staff from travelling to meet work commitments or there is a need for self-isolation |  | Capacity | Work cannot be delivered Staff unable to be in office or attend meetings | 3 | 4 | 12 | Monitor and follow government guidance Make use of tele and video conferencing All staff equipped to work from home and systems maintained to share information (dropbox, Office 365) | ALL | 2 | 3 | 8 | reducing: work being delivered, restrictions being eased | Ongoing | 2020-03-04 | 2022-03-01 | 2022-06-01
C3 |  | Sudden incapacity or departure of staff |  | Capacity | Interruption of business, Overstretch of existing staff failure to deliver on commitments | 2 | 5 | 10 | Clear procedures and workplan succession planning | Board / ED | 2 | 3 | 6 | New risk | Sudden | 2021-09-02 | 2022-03-01 | 2022-09-01
G1 | 6.c.1 6.c.4 6.f.1 | Poor governance - Board fails to efficiently discharge its duties | MG13 | Governance | Loss of credibility Legal penalties Organisation unsustainable | 2 | 4 | 8 | Review of new organisational structure Effective induction of board members Strict compliance to Articles of Association; Use only credible legal and financial services | WK/JM | 2 | 3 | 6 | Stable: adapting to new structure | Ongoing | 2019-11-11 | 2022-03-01 | 2022-09-01
G2 | 6.c | Legal liabilities - Failure to comply with legislative and regulatory requirements | MG15 | Governance | Loss of money Legal sanction Viability of organisation | 2 | 3 | 6 | Due diligence in business processes Strict compliance to Articles of Association Use only credible legal and financial services; health and safety processes; HR processes | WK/JM | 2 | 3 | 6 | Stable | Ongoing | 2019-11-11 | 2022-03-01 | 2022-11-01
G3 | 6.b.5 6.d.2 | Cataclysm (fire, flood, illness, theft) | MG17 | Governance | Interuption to business activity Temporary loss of staff Loss of equipment/resources | 2 | 4 | 8 | Take all proper contingencies for health and safety Comprehensive insurance cover Shared planning, communication and documentation for staff cover | JM | 2 | 3 | 6 | Stable | Ongoing | 2019-11-11 | 2022-03-01 | 2022-11-01
G4 | 5.d.1 | Liabilities derived from advice | Research & Practice CB9 | Governance | Loss of reputation Loss of money Legal challenge Threat to existence of organisation | 2 | 5 | 10 | Professional Indemnity Insurance Clear statement of liabilities on all advice | ALL | 2 | 3 | 6 | Risk increased by project work and consultancy | Ongoing | 2020-05-28 | 2022-03-01 | 2023-01-01
G5 |  | Implementation of charitable status creates tubulence |  | Governance | reputational damaga effort legal challenge opportunity lost | 3 | 3 | 9 | Legal advice, discussion with auditors, training for staff / board | WK | 1 | 3 | 3 | New risk | Key date: annual report 2021 | 2021-09-02 | 2022-03-01 | 2022-09-01
IM1 | 6.b.5 6.d.2 | Information management - failure to securely manage organisational records and data | MG17/New | IM | Loss of credibility; detrimental operational impact; | 2 | 4 | 8 | cyber security; effective IT policies, protection and support | WK/JM | 2 | 3 | 6 | Stable. External risks increasing but response more robust | Ongoing | 2019-11-11 | 2022-03-01 | 2022-06-01

## OPPORTUNITY REGISTER
DPC Opportunity Register (not edited)
Opportunity number | Description | Benefit | Raw Likelihood | Raw Impact | Creep | Raw Score | Barriers | Owner | Actions | Time profile | Date Recorded | Last Review | Next Review
1 | Engagement with Library, Archive Schools and related | Skilled graduate workforce Develop members' workforce New members New Revenue | 4 | 4 | 1 | 16 | lines of communication membership structure | ED / Board | open lines of communication develop new class of memnber | 2010-2012 | 2009-11-05 | 2014-04-03 | 2014-09-01
2 | Policy consultancy including accreditation | New proposition for members additional revenue stream Embed DPC as agent within national E-Infrastructure | 2 | 5 | 2 | 5 | development of accreditation tools consensus around accreditation staffing | ED/ Board | establish Task Force engage with other players eg APA, TNA, MLA, RCUK, etc Make theme of planning day recruit or second staff | 2010-2012 | 2009-11-05 | 2014-04-03 | 2014-09-01
3 | Engage in digital change management agenda | extend impact and relevance new revenue streams embed preservation within wider strategy | 3 | 4 | 3 | 4 | engaging with large community staffing risk to identity or brand | ED/Board | engage with larger knowledge management community | 2010-12 | 2009-11-05 | 2014-04-03 | 2014-09-01
4 | Grow the membership | public recognition additional revenue wider relevance and impact confidence and dynamism | 3 | 4 | 1 | 12 | contacts and proposition diminishing public purse dilutes membership overall governance restriction on vendor membership | ED/ Board | develop contacts review governance New member classes remain high profile offer great services clear member proposition | 2010-12 | 2009-11-05 | 2014-04-03 | 2014-09-01
5 | training materials | develop members' workforce raise profile demonstrate effectiveness | 4 | 4 | 1 | 16 | capacity proliferation of training perception of exclusivity | ED/ Board | commission new reports establish task force for DP manual Find publishers | 2010-12 | 2009-11-05 | 2014-04-03 | 2014-09-01
6 | RLUK members to join DPC directly | increased revenue increased skill base increased credibility | 4 | 3 | 1 | 12 | lines of communication perception of competition slow decision making | ED/ Board | open lines of communication encourage rapid decision making | 2011-14 | 2011-03-10 | 2014-04-03 | 2014-09-01