## PAW-PERS Maintenance Plan
PERS Preservation Maintenance Plan
Schedule: The next Maintenance exercise is scheduled to take place in Jan 2020. To perform the maintenance go through each of the following 17 steps.
1. Purpose: This document specifies the actions to be taken in the future to enable the contents of the PERS collection (both digital and physical) to continue to be viewed and used to a level of quality and utility not less than is possible today.
2. Previous preservation actions taken: At the point at which this document was written the following preservation actions had been taken: - Those digital items not already in PDF format, with the exception of a single MP3 sound file, had been converted to PDF, and, where appropriate, some of those files had been retained in their original formats. - Most of the physical items had been placed in presentation folders or plastic wallets and those containers had all been properly numbered and labelled. - Backup arrangements had been reviewed, documented and implemented. - The index had been reorganised to make it easier to understand and to include additional information about the collection. - Steps had been taken to try to ensure that the Index does not become separated from the items in the collection, and that users of the collection items are always aware that there is an Index and vice-versa.
3. Possible future preservation issues: At the point when the above preservation actions had been taken, the following issues were identified as possible future preservation issues: - only about 4% of the digital collection had been converted to PDF-A format because the conversion process from PDF to PDF-A was too time-consuming to perform manually and no tools had been identified to automate the process. - The items in the display case are crammed into too small a space and could easily get moved to different locations and become separated from each other. Their labelling may also not be sufficiently securely attached (this issue is to receive immediate attention).
4. How to implement this Maintenance Plan: To implement this Plan, perform the activities listed below. A description of each activity is provided in subsequent sections in this document. If a more rigorous approach is required, create a Digital Preservation Plan Description and Chart (such as the ones from which this Maintenance Plan emanated - see PERS-0073-01), after defining the conversion action to be taken. The activities are to be performed in the order they are listed below: - specify the preservation period - review the overall hardware and operating system strategy - perform an inventory check - catalogue the file types - then, for each file type: - try opening a few example files - define the application and platform strategy - define conversion action to be taken If required, create a Digital Preservation Plan Description and Chart at this point - make any changes to the Applications and Platforms that have been defined - perform any actions previously specified on the physical items and storage - then, for each file type: - implement the specified conversion action on each file - update the File Type column in the Index - review and update the next version of this maintenance plan - review and update the backup arrangements.
5. Specify the preservation period: Decide when the next Maintenance exercise after this one is to take place. This will determine the minimum period over which the collection is to be preserved by the actions taken in this maintenance exercise.
6. Review the overall hardware and operating system strategy: The ability to open and use the collection's digital files is critically dependent on the hardware and operating system platforms upon which the application software runs. Therefore, identify if any changes are planned to these platforms over the period leading up to the next maintenance exercise.
7. Perform an inventory check: Use the Index to check that all physical and digital items are in place. While doing so, identify any physical items or storage containers that are in poor condition and specify what action is to be taken to rectify the problems. Try to find any missing items. If they still can't be found, record the fact that they are missing in the Index.
8. Catalogue file types: Use a software tool such as DROID, or simply use Windows Explorer, to identify what file types are present in the collection.
9. Try opening a few example files: For each file type, take a few example files and try to open them. Make notes on what happens including what application (and its version number) is used to open the files.
10. Define the application and platform strategy: For each file type, decide what application you want to be able to open them in; then what operating system you want the application to run on; and then what hardware you want to use (it is probable that you'll want to use the same operating system and hardware platforms for all the items in the collection - but it is also possible that particular applications may influence the platform decision).
11. Define conversion action to be taken: For each file type, define what conversion, if any, is to be performed on all the files of that type; and the process and tools to be used to achieve the conversion.
12. Make any changes to the Applications and Platforms that have been defined: Before proceeding with any conversion activities, make any changes to the Hardware, Operating System and Applications that are required.
13. Perform any actions previously specified on the physical items and storage: If any problems with the physical items and storage containers had been identified while undertaking the inventory check, carry out the rectification work that has been specified.
14. Implement the conversion action on each file: For each file type perform the conversion actions that have been specified on all the files of that type. Test that the converted files open up satisfactorily before deleting the originals.
15. Update the Electronic Format column in the Index: For all the items of a particular file type that have been converted, update the Electronic Format column in the Index with the new format to which the files have been changed to.
16. Review and update the next version of this maintenance plan: Go through this document and update it as necessary with information for the next maintenance exercise. Be sure to change the date in the Schedule section at the beginning of the document and to include the date in your personal calendar. In addition, update the ' Previous preservation actions taken' and the 'Possible future preservation issues: ' sections. Modify the maintenance process if required in the light of the exercise just completed.
17. Review and update the backup arrangements: Review the backup arrangements and check they have been operating correctly. Test out the recovery of files from the different backup mechanisms. Make any changes to the backup arrangements that are needed. When all changes have been made, update the version number and date in the file name of the PERS Index document, and then make backup copies of the PERS folder.