## Action Plan
Preservation Plan Chart for PERS Collection | [5 empty] | v1.1, 27Jan2015
Designed to a) print A4 portrait without Notes column or Gantt chart
b) be sorted by Start or End date, or Owner, and to be returned to original order by sorting on Ref
Ref | Activity | Outcome | Owner | Days | Start | End | Status | Notes | 15-21Dec | 22-28Dec | 29-04Jan | 05-11Jan | 12-18Jan | 19-25Jan | 26-01Feb | 02-08Feb | 09-15Feb | 16-22Feb
1 | Convert Electronic File Formats
1.1 | Obtain PDF/A software | Updated eCopy softwre | PW | 0.2 | 2014-12-18 | 2014-12-24 | Open
1.2 | List docs needed in original form | List of Index Numbers | PW | 0.2 | 2014-12-18 | 2014-12-18 | Open | Deliverable A (List of files to be retained in original format)
1.3 | Upgrade original form docs | Files in latest versions | PW | 0.2 | 2014-12-19 | 2014-12-19 | Open
1.4 | Put original form info into Index | Updated Index doc | PW | 0.1 | 2014-12-19 | 2014-12-19 | Open
1.5 | Convert non-PDF docs to PDF/A | Set of PDF/A files | PW | 0.5 | 2014-12-31 | 2105-01-04 | Open
1.6 | Convert PDF docs to PDF/A | Set of PDF/A files | PW | 5 | 2014-12-31 | 2105-01-10 | Open | Deliverable B (Updated Electronic Files in PAW-PERS Folder)
2 | Re-organise Physical Items Storage
2.1 | Check physical items with Index | Updated Index doc | PW | 3 | 2015-01-12 | 2015-01-15 | Open
2.2 | Define physical item storage | Storage facilities list | PW | 0.8 | 2015-01-16 | 2015-01-16 | Open | Deliverable C (C. Physical storage specification document)
2.3 | Define physical item labelling | Labelling specification | PW | 0.2 | 2015-01-16 | 2015-01-16 | Open
2.4 | Obtain storage & labelling | Available storage | PW | 1 | 2015-01-17 | 2015-01-20 | Open
2.5 | Put phys storage info in Index | Updated Index doc | PW | 1 | 2015-01-17 | 2015-01-25 | Open
2.6 | Store physical items | Physical files in stores | PW | 4 | 2015-01-21 | 2015-01-25 | Open | Deliverable D (Reorganised physical items in new storage)
3 | Integrate Index into Collection
3.1 | Review layout of Index | Index revision spec | PW | 1 | 2015-01-26 | 2015-01-27 | Open | Deliverable E (Index revision specification)
3.2 | Modify Index as defined | Revised Index doc | PW | 2 | 1900-01-27 | 2015-01-29 | Open | Deliverable F (Revised Index document)
3.3 | Revise Index file name | New Index file name | PW | 0.1 | 1900-01-27 | 2015-01-29 | Open
3.4 | Include Index in Elec File folder | Index file in Elec Folder | PW | 0.1 | 1900-01-27 | 2015-01-29 | Open
3.5 | Put Index info in Phys Storage | Index info in Phys Stge | PW | 0.2 | 2015-01-30 | 2015-01-31 | Open
4 | Revise Back-up and DR Processes
4.1 | Review/define back-up process | Back-up process doc | PW | 2 | 2015-02-02 | 2015-02-04 | Open | Deliverable G (Backup and DR process definition and test plan)
4.2 | Create physical media back-ups | Populated back-ups | PW | 0.5 | 2015-02-05 | 2015-02-06 | Open
4.3 | Check Cloud back-up is working | Working cloud back-up | PW | 0.5 | 2015-02-05 | 2015-02-06 | Open
4.4 | Test Cloud re-instatement | Updated back-up doc | PW | 1 | 2015-02-07 | 2015-02-09 | Open
4.5 | Test media re-instatement | Updated back-up doc | PW | 1 | 2015-02-07 | 2015-02-09 | Open
4.6 | Create updated back-up media | Populated back-ups | PW | 0.2 | 2015-02-07 | 2015-02-09 | Open
5 | Create Preservation and Maintenance Plan
5.1 | Define Maintenance activities | Rough notes | PW | 1 | 2015-02-10 | 2015-02-11 | Open
5.2 | Document Maintenance Plan | Maintenance Plan doc | PW | 3 | 2015-02-12 | 2015-02-19 | Open | Deliverable H (Preservation Maintenance Plan)
5.3 | Create maintenance reminders | Reminders in Cal etc | PW | 0.1 | 2015-02-17 | 2015-02-19 | Open
5.4 | Update/distribute media back-ups | Distributed back-ups | PW | 0.4 | 2015-02-20 | 2015-03-09 | Open | [10 empty] | >>>>>>>>>
|  |  | Total | 29.3