## Maintenance Plan
PHOTOS Preservation Maintenance Plan
Schedule: The next Maintenance exercise is scheduled to take place in April 2020. To perform the maintenance go through each of the following 17 steps.
1. Purpose: This document specifies the actions to be taken in the future to enable the contents of the-PHOTOS collection (both digital and physical) to continue to be viewed and used to a level of quality and utility not less than was possible in 2015.
2. Previous preservation actions taken: At the point at which this document was written the following preservation actions had been taken: - The formats of all 17,000+ files comprising the digital collection had been reviewed and conversions performed to reduce them to just the following jpg, png, mp4, docx, and xlsx formats. For video items that were converted to mp4, the original mov versions were retained. - It was ensured that all videos were included on physical DVDs, and that the DVD containers were correctly labelled. - The index had been reorganised to make it easier to understand and to include additional information about the collection. - Steps had been taken to try to ensure that the main components of the collection (digital files, phyiscal photos and DVDs, negatives, and the Index) do not become separated from each other, and that users of the physical items are always aware that there are digital equivalents including an Index, and vice-versa. - A user guide had been created and briefly discusssed with the younger members of the family who would be likely to eventually come into possession of the collection. - Backup arrangements were due to be reviewed, documented and implemented immediately following the production of this document (this was left to last to ensure that this Maintenance Plan gets included in any backups taken as part of that exercise).
3. Possible future preservation issues: At the point when the above preservation actions had been taken, the following issues were identified as possible future preservation issues: - It is possible that some digital photos may be missing because it would have been too time-consuming to go through every one of the 1400+ folders to check that they contained the correct files. - Some of the physical photo albums are falling apart and may need replacing. - The negatives and original DVDs may deteriorate because no attempt was made in this preservation exercise to identify the optimum conditions for their storage.
4. How to implement this Maintenance Plan: To implement this Plan, perform the activities listed below. A description of each activity is provided in sections 5 - 17 of this document. If a more rigorous approach is required, create a Digital Preservation Plan Description and Chart (such as the ones from which this Maintenance Plan emanated - See XXX), after defining the conversion action to be taken. The activities are to be performed in the order they are listed below: - specify the preservation period - review the overall hardware and operating system strategy - perform an inventory check and identify any work required on the physical items and storage - catalogue the file types - then, for each file type: - try opening a few example files - define the application and platform strategy - define any conversion action to be taken If required, create a Digital Preservation Plan Description and Chart at this point. - make any changes to the Applications and Platforms that have been defined - perform any work previously specified on the physical items and storage - then, for each file type: - implement the specified file conversion actions - update the Format column in the Index as necessary - create the next version of this maintenance plan - review and update the backup arrangements and make new backups as necessary.
5. Specify the preservation period: Decide when the next Maintenance exercise after this one is to take place. This will determine the minimum period over which the collection is to be preserved by the actions taken in this maintenance exercise.
6. Review the overall hardware and operating system strategy: The ability to open and use the collection's digital files is critically dependent on the hardware and operating system platforms upon which the application software runs. Therefore, identify if any changes are planned for these platforms over the period leading up to the next maintenance exercise.
7. Perform an inventory check and identify any work required on the physical items and storage: Use the Index to check that all physical and digital items are in place. While doing so, identify any physical items or storage containers that are in poor condition or inadequate in any way, and specify what action is to be taken to rectify the problems. Try to find any missing items. If they still can't be found, record the fact that they are missing in the Index.
8. Catalogue file types: Use a software tool such as DROID (downloadable for free from the National Archives site in 2015), or simply use Windows Explorer, to identify what file types are present in the collection.
9. Try opening a few example files: For each file type, take a few example files and try to open them. Make notes on what happens including what application (and its version number) is used to open the files.
10. Define the application and platform strategy: For each file type, decide what application you want to be able to open them in; then what operating system you want the application to run on; and then what hardware you want to use (it is probable that you'll want to use the same operating system and hardware platforms for all the items in the collection - but it is also possible that particular applications may influence the platform decision).
11. Define conversion action to be taken: For each file type, define what conversion, if any, is to be performed on all the files of that type; and the process and tools to be used to achieve the conversion.
12. Make any changes to the Applications and Platforms that have been defined: Before proceeding with any conversion activities, make any changes to the Hardware, Operating System and Applications that are required.
13. Perform any work previously specified on the physical items and storage: If any problems with the physical items and storage containers had been identified while undertaking the inventory check, carry out the rectification work that has been specified.
14. Implement the conversion action on each file: For each file type perform the conversion actions that have been specified on all the files of that type. Test that the converted files open up satisfactorily before deleting any originals. Consider retaining the originals to mitigate against any reduction in quality introduced during major conversions from one format to a completely new format (as opposed to just updating the version of a particular format).
15. Update the Format column in the Index: For all the items of a particular file type that have been converted, update the Format column in the Index with the name of the new format to which the files have been changed.
16. Review and update the next version of this maintenance plan: Go through this document and update it as necessary with information for the next maintenance exercise. Be sure to change the date in the Schedule section at the beginning of the document and to include the date in your personal calendar. In addition, update the ' Previous preservation actions taken' and the 'Possible future preservation issues: ' sections. Modify the maintenance process steps if required as a result of experience gained in the exercise just completed.
17. Review and update the backup arrangements: Review the backup arrangements and check they have been operating correctly. Test out the recovery of files from the different backup mechanisms. Make any changes to the backup arrangements that are needed. When all changes have been made, check that the Index file worksheet on backup arrangements is completely up to date, and then ensure that the latest versions of all the electronic components of the PHOTOS collection are backed up.
ENDS